## projects_2023
Start_Date | End_Date | Project | Task | Owner | Resources | Status | Comments
2023-01-01 | 2023-01-15 | Automation Clients | Finish on going reports | David Alegria | 1 | Paused | 30 reports to do
2023-01-15 | 2023-02-28 | Automation Clients | Finish not started | David Alegria | 1 | Not started | 30 reports to do
2023-01-01 | 2023-02-28 | Migration DWH | Finish not initial scope | Rui Cabeça | 1 | Not started | After March, 1 FTE to give support
2022-11-01 | 2023-04-30 | Migration DWH | Support Deposte | Rui Cabeça | 1 | On going | After March, 1 FTE to give support
2023-01-01 | 2023-12-31 | Handover Operations | Handover Operations | Paulo Costa | 1 | Paused | 40 reports to do (4 per month)
2023-03-01 | 2023-05-01 | Pack Standard Clients | Pack Standard Clients | David Alegria | 1 | Not started | Standard pack to clients
2023-05-01 | 2023-12-31 | Pack Standard Clients Tableau | Pack Standard Clients Tableau | Paulo/David | 1 | Not started | Introduce Tableau to clients

## FTE
Month | Migration | Reports/month | Automation Clients | Reports/month.1 | Handover Ops | Reports/month.2 | Pack Clients | Reports/month.3 | Tableau Pack Clients | Reports/month.4 | Follow-up Automation | Unnamed: 12 | FTE Projects | FTE BAU | FTE Tilden | Total FTE
2023-01-01 | 1 |  | 1 | 15 | 1 | 3 | [6 empty] | 3 | 2 | 1 | 6
2023-01-02 | 1 |  | 1 | 15 | 1 | 3 | [6 empty] | 3 | 2 | 1 | 6
2023-01-03 | 1 |  |  |  | 1 | 3 | 1 | [5 empty] | 3 | 2 | 1 | 6
2023-01-04 | 1 |  |  |  | 1 | 3 | 1 | [5 empty] | 3 | 2 | 1 | 6
2023-01-05 |  |  |  |  | 2 | 6 |  |  | 1 | 1 |  |  | 3 | 2 | 1 | 6
2023-01-06 |  |  |  |  | 2 | 6 |  |  | 1 | 1 |  |  | 3 | 2 | 1 | 6
2023-01-07 |  |  |  |  | 2 | 6 |  |  | 1 | 1 |  |  | 3 | 2 | 1 | 6
2023-01-08 |  |  |  |  | 2 | 6 |  |  | 1 | 1 |  |  | 3 | 2 | 1 | 6
2023-01-09 |  |  |  |  | 2 | 6 |  |  | 1 | 1 |  |  | 3 | 2 | 1 | 6
2023-01-10 | [8 empty] | 1 | 1 | 1 |  | 2 | 3 | 1 | 6
2023-01-11 | [8 empty] | 1 | 1 | 1 |  | 2 | 3 | 1 | 6
2023-01-12 | [8 empty] | 1 | 1 | 1 |  | 2 | 3 | 1 | 6