## projects_2023
Start | Finish | Parent | Task | Owner | Resource | Resources | Comments
2023-01-01 | 2023-02-28 | Automation Clients | Automation Clients | David Alegria | Incomplete | 1 | 30 reports to do
2023-01-01 | 2023-02-28 | Migration DWH | Migration DWH | Rui Cabeça | Incomplete | 1 | After March, 1 FTE to give support
2023-01-01 | 2023-04-30 | Migration DWH | Migration DWH | Rui Cabeça | Incomplete | 1 | After March, 1 FTE to give support
2023-01-01 | 2023-12-31 | Handover Operations | Handover Operations | Paulo Costa | Incomplete | 1 | 40 reports to do (4 per month)
2023-03-01 | 2023-05-01 | Pack Standard Clients | Pack Standard Clients | David Alegria | Incomplete | 1 | Standard pack to clients
2023-05-01 | 2023-12-31 | Pack Standard Clients Tableau | Pack Standard Clients Tableau | Paulo/David | Incomplete | 1 | Introduce Tableau to clients

## FTE
Month | Migration | Reports/month | Automation Clients | Reports/month.1 | Handover Ops | Reports/month.2 | Pack Clients | Reports/month.3 | Tableau Pack Clients | Reports/month.4 | Follow-up Automation | Unnamed: 12 | FTE Projects | FTE BAU | FTE Tilden | Total FTE
2023-01-01 | 1 |  | 1 | 15 | 1 | 3 | [6 empty] | 3 | 2 | 1 | 6
2023-01-02 | 1 |  | 1 | 15 | 1 | 3 | [6 empty] | 3 | 2 | 1 | 6
2023-01-03 | 1 |  |  |  | 1 | 3 | 1 | [5 empty] | 3 | 2 | 1 | 6
2023-01-04 | 1 |  |  |  | 1 | 3 | 1 | [5 empty] | 3 | 2 | 1 | 6
2023-01-05 |  |  |  |  | 2 | 6 |  |  | 1 | 1 |  |  | 3 | 2 | 1 | 6
2023-01-06 |  |  |  |  | 2 | 6 |  |  | 1 | 1 |  |  | 3 | 2 | 1 | 6
2023-01-07 |  |  |  |  | 2 | 6 |  |  | 1 | 1 |  |  | 3 | 2 | 1 | 6
2023-01-08 |  |  |  |  | 2 | 6 |  |  | 1 | 1 |  |  | 3 | 2 | 1 | 6
2023-01-09 |  |  |  |  | 2 | 6 |  |  | 1 | 1 |  |  | 3 | 2 | 1 | 6
2023-01-10 | [8 empty] | 1 | 1 | 1 |  | 2 | 3 | 1 | 6
2023-01-11 | [8 empty] | 1 | 1 | 1 |  | 2 | 3 | 1 | 6
2023-01-12 | [8 empty] | 1 | 1 | 1 |  | 2 | 3 | 1 | 6