## projects_2023
Start_Date | End_Date | Project | Task | Owner | Resources | Status | Comments
2023-01-01 | 2023-01-15 | Automation Clients | Finish on going reports | David Alegria | 1 | Paused | 20 to finish
2023-01-15 | 2023-02-28 | Automation Clients | Finish not started | David Alegria | 1 | Not started | 30 reports to do
2023-01-01 | 2023-04-30 | Handover Operations | Handover Operations Phase I | Paulo Costa | 1 | Paused | 1 FTE
2023-04-30 | 2023-09-30 | Handover Operations | Handover Operations Phase II | Paulo Costa | 2 | Paused | 2 FTE
2023-02-01 | 2023-03-31 | Migration DWH | Finish not initial scope | Rui Cabeca | 1 | Not started | Until March, 1 FTE to give support
2022-11-01 | 2023-03-31 | Migration DWH | Support Deposte | Rui Cabeca | 1 | On going | Until March, 1 FTE to give support
2023-01-01 | 2023-02-28 | Migration DWH | Migarte reports from Deposte | Rui Cabeca | 1 | Not started | Until March, 1 FTE to give support
2023-03-01 | 2023-03-31 | Pack Standard Clients | Pack Standard Clients | David Alegria | 1 | Not started
2023-04-01 | 2023-04-30 | Pack Standard Clients Tableau | Check interest of Clients | Paulo/David | 1 | Not started
2023-04-01 | 2023-04-30 | Pack Standard Clients Tableau | Define requirements for standard reports | Paulo/David | 1 | Not started | Template...
2023-05-01 | 2023-05-31 | Pack Standard Clients Tableau | Create and introduce to Tilden Park 1st report | Paulo/David | 1 | Not started
2023-06-01 | 2023-08-31 | Pack Standard Clients Tableau | Create reports Phase I | Paulo/David | 1 | Not started
2023-09-01 | 2023-12-31 | Pack Standard Clients Tableau | Create reports Phase II | Paulo/David | 2 | Not started
2023-10-01 | 2023-10-15 | Performance Optimization | Assesment templates and processes | Paulo | 1 | Not started | Check templates and processes to be worked on
2023-10-15 | 2023-12-31 | Performance Optimization | Improving of templates and processes | Paulo | 1 | Not started

## FTE
Month | Migration | Reports/month | Automation Clients | Reports/month.1 | Handover Ops | Reports/month.2 | Pack Clients | Reports/month.3 | Tableau Pack Clients | Reports/month.4 | Performance Optimization | Unnamed: 12 | FTE Projects | FTE BAU | FTE Tilden | Total FTE
2023-01-01 | 1 |  | 1 | 15 | 1 | 3 | [6 empty] | 3 | 2 | 1 | 6
2023-01-02 | 1 |  | 1 | 15 | 1 | 3 | [6 empty] | 3 | 2 | 1 | 6
2023-01-03 | 1 |  |  |  | 1 | 3 | 1 | [5 empty] | 3 | 2 | 1 | 6
2023-01-04 | 1 |  |  |  | 1 | 3 |  |  | 1 |  |  |  | 3 | 2 | 1 | 6
2023-01-05 |  |  |  |  | 2 | 6 |  |  | 1 | 1 |  |  | 3 | 2 | 1 | 6
2023-01-06 |  |  |  |  | 2 | 6 |  |  | 1 | 1 |  |  | 3 | 2 | 1 | 6
2023-01-07 |  |  |  |  | 2 | 6 |  |  | 1 | 1 |  |  | 3 | 2 | 1 | 6
2023-01-08 |  |  |  |  | 2 | 6 |  |  | 1 | 1 |  |  | 3 | 2 | 1 | 6
2023-01-09 |  |  |  |  | 2 | 6 |  |  | 1 | 1 |  |  | 3 | 2 | 1 | 6
2023-01-10 | [8 empty] | 1 | 1 | 1 |  | 2 | 3 | 1 | 6
2023-01-11 | [8 empty] | 1 | 1 | 1 |  | 2 | 3 | 1 | 6
2023-01-12 | [8 empty] | 1 | 1 | 1 |  | 2 | 3 | 1 | 6

## summary
FTE
Month | Migration | Automation Clients | Handover Ops | Pack Clients | Tableau Pack Clients | Performance Optimization | FTE Projects | FTE BAU | FTE Tilden | Total FTE
2023-01-01 | 1 | 1 | 1 |  |  |  | 3 | 2 | 1 | 6
2023-01-02 | 1 | 1 | 1 |  |  |  | 3 | 2 | 1 | 6
2023-01-03 | 1 |  | 1 | 1 |  |  | 3 | 2 | 1 | 6
2023-01-04 | 1 |  | 1 |  | 1 |  | 3 | 2 | 1 | 6
2023-01-05 |  |  | 2 |  | 1 |  | 3 | 2 | 1 | 6
2023-01-06 |  |  | 2 |  | 1 |  | 3 | 2 | 1 | 6
2023-01-07 |  |  | 2 |  | 1 |  | 3 | 2 | 1 | 6
2023-01-08 |  |  | 2 |  | 1 |  | 3 | 2 | 1 | 6
2023-01-09 |  |  | 2 |  | 1 |  | 3 | 2 | 1 | 6
2023-01-10 |  |  |  |  | 2 | 1 | 3 | 2 | 1 | 6
2023-01-11 |  |  |  |  | 2 | 1 | 3 | 2 | 1 | 6
2023-01-12 |  |  |  |  | 2 | 1 | 3 | 2 | 1 | 6